## Time Log
Modiin4u — Time Log
Arvindra Singh · GTS Infosoft
Date | Day | Area | Work done | Hours | Status
2026-08-11 |  | Setup | Project set up; 24 screens scaffolded across events, real estate, community, deals, games, steps, parking and admin | 4 | Done
2026-08-12 |  | App shell | Onboarding, search, dark mode, community feed; real estate rebuilt from Figma; auth screens and map | 6 | Done
2026-08-28 |  | Admin panel | Admin dashboard built out — 23 sections with their screens; analytics dashboard; images on articles and businesses | 5 | Done
2026-09-14 |  | Web + screens | Web production pages: homepage, real estate, listing detail. New screens for auth, restaurants, events map. Platform configs, icons, splash | 7 | Done
2026-09-15 |  | Web | Real estate search for sale and rent, web layout | 3 | Done
2026-09-16 |  | Content import | Directory, news, restaurants and map pulled from the WordPress export; desktop pages for deals, events, news, municipal; shared navbar and footer | 8 | Done
2026-09-18 |  | Content import | Every article bundled and every category exposed | 3 | Done
2026-09-20 |  | Database | SQL seed generated from the WordPress export | 3 | Done
2026-09-23 |  | Live data | News, businesses, restaurants, events, map and search moved onto the live database — 200 businesses and 659 articles with their photographs | 4 | Done
2026-09-23 |  | App quality | Loading states matched to the real layout; back button fixed across the app; scrolling freed to the screen's full refresh rate; fonts bundled instead of downloaded | 2 | Done
2026-09-23 |  | Accounts | Sign-in, sign-up, forgot and change password on Supabase; account deletion; notification preferences; access controls; saved favourites | 3 | Done
2026-09-23 |  | Maps | Google Maps on the client's key, with the app's own markers; key kept out of the repository | 1.5 | Done
2026-09-23 |  | Admin panel | Control centre moved onto live data — 21 sections; opening hours editor; category picker; image upload; safe delete | 4 | Done
2026-09-23 |  | Database | Migrations for security, sign-in, notifications, media storage and the real estate schema | 2 | Done
2026-09-23 |  | Languages | Hebrew and English with a working switch; sign-in and settings translated | 1.5 | Done
Total hours
How to use
Add one row per block of work. Type the date in column A — the day fills in by itself.
Hours are in decimals: 90 minutes is 1.5.
Status is a dropdown: Done, In progress, Blocked, On hold.
The summary tab adds itself up from this one — nothing to keep in step by hand.

## Summary
Summary
By area
Area | Hours | Share
Accounts
Admin panel
App quality
App shell
Content import
Database
Languages
Live data
Maps
Setup
Web
Web + screens
Total
By day
Date | Hours | Entries
2026-08-11
2026-08-12
2026-08-28
2026-09-14
2026-09-15
2026-09-16
2026-09-18
2026-09-20
2026-09-23
Both tables read the Time Log tab, so adding a row there updates them.